## Sheet1
Test Plan
Feature to be tested (In Scope) |  | Estimation
1. Sign UP |  | 1. Sign UP : 1 hours
2. Sign In |  | 2. Sign In : 1 hours
3. Create Account |  | 3. Create Account : 2 hours
Feature not to be tested (In Scope) |  | Staffing & Training
1. Edit Account Info |  | Staffing
2. Create Multiple Account |  | 1. Manual testing : Arpita Paul | ting | Sharmin Sultana
Test Leaves & Test Types |  | Training
1. Manual Testing : Professional Manual Testing, Udemy
Test Levels
1. System Testing |  | Accumulations
2. Acceptance testing
1. Front end & Back end Developers, Deliver the code related to the feature
Test Types
1. Functional Testing |  | Risk
2. Usability Testing
3. Regression Testing |  | List of Risk
1. Risk 1 : Late Delivery for features
Exit Criteria |  | 2. Risk 2 : QA Environment is down
3. Risk 3 : Unplanned Vacations
1. Testing is finish and there are no functional bugs |  | 4. Risk 4 : Critical bugs keep showing which affect the time frame
2. All Remaining Bugs have low severity
3. No more than 10% of medium-severity bugs are open |  | Risk Mitigation
1. Risk 1: Accepted
Suspension Criteria |  | 2. Risk 2: Transfer
3. Risk 3: Monitoring
1. Critical bugs are open and they are blocking testing |  | 4. Risk 4: Acceptance
2. All remaining test case are blocking by one open bug
Test Reference
Test Deliverable
1. User Stories
1.Test plan |  | 2. Figma Design
2. Bug Report |  | 3. System Design
3. Summary Report
4. Test case
Test Environment
1. Operating System : Linux
2. Server: Production
3. Browser: Chrome
4. Network: WiFi